# FFAR Final Progress Report

As part of closing out a FFAR grant, grantees must complete a Final Progress Report. Please use the template below to complete the programmatic report. The report must be submitted to FFAR within 90 days after the expiration or termination of a FFAR funded research grant. All questions about this form should be directed to grants@foundationfar.org.

The Final Progress Report communicates the cumulative results and major accomplishments of the funded grant research, including accomplishment for each aim and whether all research aims were fully completed. FFAR uses the content of the Final Progress Report to inform Congress, the Advisory Board, and other stakeholders on the successes, impacts and value of funding unique partnerships to support innovative science addressing today’s food and agriculture challenges. If a question is not applicable to the project, please type “Nothing to report.”

| Grant Information |  |
| --- | --- |
| Grant ID | 41000769 |
| Award Program | Plant Protein Enhancement (PPE) |
| Project Title | Capitalizing on the unique viscoelastic properties of corn zein for a new commercial plant-based protein |
| Grant Start Date | 04/01/2020 |
| Grant End Date | 03/31/2023 |
| Total Grant Budget | $387,556.16 |
| Total FFAR Budget | $387,556.16 |
| Matching Funder(s) | None |
| Final Report Date | 07/01/2023 |
| Project Director/Principal Investigator Information |  |
| Full Name | Bruce R. Hamaker |
| Email | hamakerb@purdue.edu |
| Phone | 765-494-5668 |
| Grantee Organization Information |  |
| Organization Name | Purdue University |
| Address | 155 South Grant St |
| City, State Zip | West Lafayette, IN 47907 |
| Tax ID | 35-6002041 |
| Authorized Signing Official (ASO) Information |  |
| Name | Jason Spall |
| ASO Title | Assistant Director, Post-Award |
| Email | spsacctmgmt@purdue.edu |
| Phone | 765-494-1055 |

- General Information

  - Please list the geographic location(s) – city, state, congressional district - where  the work was conducted. If the work was conducted outside of the US, please list the city and country.

West Lafayette, IN, District 4, USA

  - How many new jobs were created because of this grant funding?

Two jobs (one post-doc and one master’s student) were created with this grant funding.

  - How many jobs were maintained because of this grant funding?

The post-doc was able to maintain his job throughout the project (3 years including 1-year NCE) and the master’s student maintained his research assistant position until his graduation (2 years).

  - Have there been any changes to your organization’s IRS 501(c)(3) non-profit status since you were awarded the grant? If yes, please explain.

No.

  - Has your organization undergone a recent name change? If so, please provide the new name of your organization.

No.

# Scientific Report

  - Public Abstract (up to 500 words): The abstract should be ‘stand-alone’ and is intended for a general audience. It should be a concise overview/summary of the importance of the project, the issues that the project addressed, and the key findings of the project. The abstract should also clearly state how the results of the project help to address important needs in U.S. food and agriculture systems.

Overview/Importance of the project/Addressed issue: Recent awareness related to health concerns and environmental sustainability issues have led to increase in consumer interest and purchases of plant-based protein products. There have been many investments and new plant-based alternatives. However, improvements still need to be made regarding the quality of products (e.g., texture, flavor, and color) to get closer to or match that of animal-source-based products. Specifically, forming desired or similar textural properties has become one of the biggest challenges. To enable this, advanced and novel technologies (e.g., high-moisture extrusion and shear-structuring), as well as functional ingredients (e.g., binding/viscoelastic agents, crosslinkers), have been introduced by the industry to provide meat-like textures to analogue products. Even though the texture-related problems of cohesiveness and viscoelasticity of meat alternatives have been resolved to some extent with use of methylcellulose or wheat gluten, there is still a search for natural and chemically-free ingredients to align with a desire for “clean label” products. In this project, we show that corn zein can be used to provide improved textural properties (specifically by creating internal cohesive and viscoelastic protein networks) to plant-based analogues instead of currently used ingredients.

Key findings: A systematic investigation was conducted to test the compatibility and interaction of zein with different proteins (soy, pea, pumpkin seed, rice, and chickpea) and filler materials (corn, wheat, and rice starches). Pea protein and rice starch, as a base protein and a filler material, were found to combine well with zein for good functionality and were used for further investigations. The formulation blends (i.e., ratios of ingredients, water content) and process variables (i.e., mixing temperature and time) were optimized to produce plant-based analogue formulations. Alkaline agents were found to significantly improve cohesiveness and elasticity (increasing with increasing concentrations). Specifically, calcium hydroxide (GRAS item), a low cost and commonly used alkaline agent in foods, was found to help zein form fibrous structures and form a dispersed network within the pea protein-carbohydrate ingredient mixture. By changing the concentration of calcium hydroxide, formulations were designed to match the textural and rheological properties of different commercial products (soft and hard cheeses, fish products, chicken nuggets, and burger patties). High-moisture extrusion was then successfully used to produce chicken nugget-like prototypes using the formulation containing zein along with pea protein, rice starch, and calcium hydroxide.

Importance to address needs in U.S. food and agriculture systems: Plant-based protein products still lack in many of the functional properties of animal-based ones to make them truly competitive in the marketplace. In this project, a new technology was developed to disperse zein protein into a base protein-carbohydrate formulation to create cohesive and viscoelastic materials that mimic a range of real-life animal-source-based commercial products, which also respond to consumers’ “clean label” desires.

  - Provide a description or interpretation of how the key findings of the project can be used by the agriculture community. It is important the PI identifies how these findings have been, or may be, adopted or adapted in U.S. agriculture and food systems. If the findings cannot yet be applied, this section should address how they can be used to guide future planning or decision-making (up to 1,000-word limit).

Meat and cheese analogues made of plant proteins are increasing in the marketplace, driven by consumer desire to consume less red meats, a move by some to vegetarian and vegan diets, consideration that production of plant proteins is more sustainable for the planet, as well as ethical and religious motivations. Additionally, many others who consume foods containing animal proteins have no problem with partial switching to plant proteins provided the quality of these products in terms of texture and flavor is good. For example, it has been reported that 95% of the people who bought a plant-based burger in 2019 were meat eaters (Curry, 2019). Regardless the reason, recent reports clearly show that the demand of plant-based foods has increased, from 8% in 2017 to about 20% last year (Curry, 2019).

Commercial products developed to satisfy the growing demand of these novel foods are now in many product markets, including burgers (e.g., Impossible Burger and Beyond Burger) where notable innovation moved rapidly from research to the commercial phase. Despite the fast developments, frequent changes in the formulations indicate that achieving good functionality with different ingredients is not a trivial task. Other legume proteins, including chickpea, lentils and a variety of beans are being investigated but many of them, like pea proteins, have good functional properties, but lack a viscoelastic structuring function. Our main finding regarding the use of corn zein protein in plant-based products as a viscoelastic and cohesive agent, is a novel way to improve plant-based protein formulations while avoiding “clean label” issues for ingredients such as methylcellulose or wheat gluten with sensitivity issues for some consumers.

High-moisture extrusion contributes to functionalities (e.g., expansion, texturization, shaping) and the formation of desired structures through denaturation of proteins and formation of new chemical bonds between proteins and other ingredients. To provide these effects and allow production of well-structured products, the design (e.g., screws, kneading elements, cooling die) and operating parameters should be taken into account. Here, we also optimized the extrusion parameters (e.g., moisture content, barrel temperatures, screw speed, cooling die temperatures, feed flow rate) for the production of high quality products, which forms the basis for further research studies.

  - Research Outcomes/Impact (up to 1,500-word limit). The primary goal here is to answer questions such as “How did this project lead to improvements in U.S. agriculture and food systems?” or “How can the findings of this study guide or make improvement in future investigations and research?” Outcomes should be explained and classified in one of the following ways:

    - potential outcomes, i.e., findings, results, or recommendations that could impact U.S. agriculture and food systems, if used;

In achieving the objectives of this proposal, we have accelerated innovation in the area with direct applications focused on improved plant-based protein products that could lead to their increased demand. At the same time, we have used our gained expertise on zein to develop fundamental and innovative research that could be directly translated to other similar systems (e.g., gluten-free formulations), as well as new plant-based protein foods (a neutral flavored spreadable protein paste with potential for flavor/nutritional additions). The structure-function methodologies used and developed for the zein blend characterization could further be used in fundamental science-based application studies in other plant protein systems, and in itself represent an innovation. Extrusion processes are currently used in the industry, but mostly using a trial-and-error approach. The systematic approaches used in this work cold extend to extruded texturized zein-based or zein-complemented prototype materials. Linking our fundamental research on rheology, and secondary structure transformations to texturized material properties (i.e., textural attributes) forms the basis for further applications in plant-based protein products.

    - b. intermediate outcomes, i.e., how the findings, results, or recommendations have been used by others to influence practices, legislation, research/product design, training and so forth; and

    - c. end outcomes, i.e., how findings, results, or recommendations have contributed to documented reductions in work-related morbidity, mortality, and/or exposure.

  - What were the goals/specific aims of the project? If the approved application lists milestones/target dates for important activities or phases for this reporting period, identify these milestones and dates, as well as show actual completion dates or the percentage of completion of milestone targets. (up to 1,500-word limit)

The major and the minor milestones in the proposal with the expected investigation periods are listed below. For each milestone, a note is included regarding the progress (full or percentage of completion) at the specified completion dates.

- Optimize the elimination of the yellow color and corn scent from zein – (target, 0-6 months; completion, on time)

- Optimize zein blends for concentration and ratios of other constituents using a lab-scale former extruder – (target, 3-21 months; completion, ~ in 24 months)

- Extend knowledge of different filler materials/commercial proteins and co-proteins/fatty acids as β-sheet “stabilizers” in the formation and stability of viscoelastic zein blends (Tg and secondary structure analyses) – (target, 3-15 months; completion, on time)

- Form dispersed web-like zein viscoelastic networks in blends – (target, 6-18 months; completion, ~ in 20 months)

- Change the zein structure to affect functional properties, mainly rheological properties – (target, 9-21 months; completion, ~ in 24 months)

Note: This milestone with its minors was completed 3 months later than was anticipated.

- Create texturized zein blends using a twin-screw extruder and cooling texturizing die – (target, 15-24 months; completion, ~ in 36 months)

Note: Due to a big delay in delivery of high moisture extruder with a cooling die (expected to arrive in August 2021 but arrived in May 2022 due to supply chain problems upon pandemic), we started this milestone one year later than the anticipated. Thus, we requested 1 year of NCE in total (2 6-month NCEs) during the project duration. This problem led to one year delay in completion of this milestone and the overall project.

  - Have any of the major goals/specific aims or milestones for the project changed since the award? If so, please list the goal(s) that have changed and provide justification for the change from the approved goals. (up to 500-word limit)

No change in any of them.

  - What was accomplished under the goals/specific aims or milestones for the project? Please describe in detail, 1) major activities; 2) specific objectives; 3) significant results, including major findings, developments, or conclusions (both positive and negative); and 4) key outcomes or other achievements. Include discussion of stated goals not met. The emphasis in reporting in this section should focus on accomplishments. In the response, emphasize the significance of the findings to the scientific field. This section can be as technical as the PI would like. (up to 5,000-word limit)

- Major activities:

- Optimization of elimination of the yellow color and corn scent from zein

  - Different methods (i.e., activated charcoal method, ethanol precipitation) and the experimental conditions of these methods (e.g., temperature, ethanol/zein ratio, storage duration) were tested.

- Optimization of formulations to be used in plant-based analogues

  - Additional ingredients (i.e., base protein and filler materials) were tested and chosen depending on their rheological properties.

  - Additional modifiers (i.e., alkaline agents: calcium hydroxide, arginine; conditions: incubation and mixer temperature) were tested to improve the degree of viscoelasticity and cohesiveness of the formulations.

  - Created formulations (i.e., pea protein, zein, rice starch, vegetable oil, calcium hydroxide, water) were investigated for their chemical (with FT-IR), viscoelastic (with rheometer), and textural (with texture analyzer) properties as well as morphology (with SEM) and 3D network formation (with confocal).

  - Textural attributes of the plant-based protein mixture were matched to those of commercial animal-source-based products, including burger patties, chicken nuggets, soft and hard cheeses, and fish, by changing the ingredient concentrations in the formulation.

- Production of texturized zein-containing pea protein-based prototypes was done using a twin-screw high-moisture extruder and cooling texturizing die.

  - Extrusion parameters (e.g., moisture content, barrel temperatures, screw speed, cooling die temperatures, feed flow rate) were tested to form well-structured prototypes.

  - Product formulations created earlier were slightly modified for extrusion conditions.

  - Produced prototypes were tested for their physicochemical, textural, rheological, and morphological properties.

- Specific objectives:

- Optimization of decolorization/deodorization of corn zein

- Finding complementing ingredients (i.e., base protein, filler material, modifying agent) to zein to be used in plant-based protein formulations.

- Optimization of ingredient concentrations and ratios to fully disperse zein into other constituents (pea protein and rice starch).

- Investigation of ways to control the degree of viscoelasticity and cohesiveness in the blends to be used in different plant-based products

- Developing blend formulations to be used in different plant-based protein products, including meat and cheese analogues

- Creation of well-structured texturized zein-containing prototypes

- Significant results/major findings:

- Activated charcoal effectively deodorized and decolorized the commercial zein, and this method was superior to the other methods tested.

- Different plant-based proteins (soy, pea, pumpkin seed, rice, chickpea, and their combination in equal amounts), as the base protein in the formulation, were tested to investigate the compatibility and interaction of these proteins with zein. It was found that while zein could be very well-dispersed into pea and chickpea proteins, it aggregates with soy and rice proteins, resulting in tough texture. For further investigations, pea protein was chosen as the base protein for formulation development.

- Different filler materials, mainly different origin of starches (corn, wheat, and rice), were studied to improve the performance of blend formulations (i.e., viscoelasticity and cohesiveness). In small and large deformation tests, rice starch was found to improve significantly the functionality of the zein-pea protein blend, resulting in formulations with similar rheological properties to wheat dough (i.e., low phase angle value, high complex modulus, and high extensional viscosity), implying an elastic material with high strength and resistance to deformation. Rice starch also significantly lowered glass transition temperature of zein blend, associated with improved performance even at room temperature. Combining zein with a proper starch type, and in cases co-proteins, substantially improved rheological properties of the zein-pea protein blend similar to that of wheat, with potential implications to the gluten-free and the plant-based protein market.

- After choosing the base protein (pea protein) and filler material (rice starch), a systematic investigation (at different ratios and with different water contents) was conducted to optimize blend formulations (zein with pea protein and rice starch) that could be used in plant-based protein analogues. We found that zein, as low as 10% on dry basis in the whole composition, can provide viscoelastic behavior to the blend with rice starch (around 25% on dry basis). This new type of formulation including zein and starch has not been reported before.

- Potential improvements in the viscoelastic properties of zein blends through the addition of alkaline agents were investigated. Small deformation tests showed that arginine and/or calcium hydroxide addition to zein-pea protein blends significantly increased elasticity and cohesiveness. Arginine did not perform as well as calcium hydroxide to provide strength to pea protein, though its effect on improving elasticity was good. A lubricated squeezing flow test showed that all blends had strain rate thickening/hardening behavior and blends were highly resistant even at higher deformation rates. Textural attributes of the blends were able to be modified with combination treatments to achieve different textural product specifications. Secondary structure composition analysis by FT-IR emphasized the importance of beta-sheet content in enhancing the material viscoelastic properties. Arginine and calcium hydroxide-incorporated blends presented the highest beta-sheet content. Imaging on blends using scanning electron and confocal microscopy showed that zein formed viscoelastic fibrils holding the structure together through a dispersed network. In conclusion, zein with an added alkaline agent provides cohesiveness and viscoelasticity to plant-based formulations for potential replacement of currently used chemically-modified hydrocolloids or wheat gluten in formulations for meat substitutes, such as analogues of chicken tenders, burger patties, and hotdogs. Calcium hydroxide was chosen for further investigations considering its high potential to further improve texture and its low cost.

- In contemplation of matching textural properties of commercial meat and cheese products with our blend formulations, calcium hydroxide concentration in the zein-pea protein-rice starch formulation was altered (0-7% of the solution or 0-3.5% of the total amount). Previous work had suggested that calcium ions bind to protein and starch in alkaline conditions due to ionization of hydroxyl groups. Weak frequency dependence and higher storage modulus compared to loss modulus suggested solid-like behavior in the dough-like blends, possessing a strong and elastic inner network that retained energy inside the structure rather than dissipating it. Imaging using scanning electron and confocal microscopies showed well-incorporated web-like networks of zein conferring the viscoelastic and cohesive structure. Infrared spectroscopy (FT-IR) showed that calcium hydroxide addition at various levels (1-7% in solution) had no significant effect on the product’s molecular and structural chemistry. A high amount of β-sheet structure was found in all formulations, resulting in good viscoelastic characteristics. Notably, textural properties (i.e., hardness, chewiness, gumminess) of the formulated ingredient blends could be matched to those of tested commercial products by changing the calcium hydroxide concentration (1%-tilapia fish, 3%-chicken nugget and mozzarella cheese, 5%-tuna fish and colby cheese, 7%-burger patties). Practical outcomes are formulations of new plant-based analogues that match the textural properties of existing animal-source-based commercial products.

- For the second phase of the project, upon optimization of process variables, high-moisture extrusion was successfully implemented to produce product prototypes. Extrusion of blends led to conformational changes in protein structure, that were reflected in the generated network and their texturization degree. Unlike our earlier findings (which only investigated the addition of rice starch to the blend at room temperature), the addition of rice starch to the formulation during extrusion lowered the strength, stiffness, elasticity and hardness of the products This behavior could be related to the higher water holding capacity of starch at higher temperatures, which can be desired for the generation of a juicier product with a soft structure. With an increase in zein content, the formation of a fibrous structure was improved. This was likely due to higher β-sheets contents. Having this fibrous structure in microscale led to formation of a layered structure with a 3D network, similar to that generated by gluten. These results encourage the utilization of zein and rice starch for the generation of gluten-free plant-based products with distinctive characteristics by high moisture extrusion technology.

- Key outcomes or other achievements:

- The textural attributes of commercial products could be matched by our new plant-based formulation blends.

- The formulations (containing zein along with pea protein and rice starch) were successfully able to produce plant-based texturized prototypes using high-moisture extrusion.

  - Discuss efforts taken to ensure the approach is scientifically rigorous. Include approaches taken to ensure robust and unbiased results.

Experimental designs were used with strong controls, replications, and preliminary testing of procedures to assure statistical rigor and unbiased results.

  - List key stakeholders that could be served by results of this project.

The outputs of this project are directly relevant to the plant-based protein food industry in the area of meat and cheese analogues. Also, the scientific community has and will benefit through publications and conference presentations describing new basic and applied findings on improvements in plant-based protein textural properties.

  - How have the results of this reporting period been disseminated to communities of interest? Describe how the results have been disseminated to communities of interest. Include any outreach activities that have been undertaken to reach members of communities who are not usually aware of such activities, to enhance public understanding and increase interest in learning and careers in science, technology, and the humanities. Reporting the routine dissemination of information (e.g., websites, press releases) is not required. For awards not designed to disseminate information to the public or conduct similar outreach activities, a response is not required; the grantee should write “nothing to report.” A detailed response is only required for awards or award components that are designed to disseminate information to the public or conduct similar outreach activities. Note that scientific publications and sharing research sources will be reported under Information Products. (up to 1,000-word limit)

Nothing to report.

  - Describe challenges or delays encountered during project and actions that were taken to resolve them. Only describe significant challenges that may have impeded the research and emphasize their resolution. (up to 500-word limit)

There was a big delay in delivery of the high moisture extruder with a cooling die, which was expected to arrive in August 2021 but arrived in May 2022 due to supply chain problems upon pandemic. Thus, the second phase of the project (producing plant-based prototypes) could not be started in its expected time, which was the reason why we requested 2 6-month NCEs for the completion of the project.

  - What opportunities for training and professional development has the project provided during this reporting period? If the research is not intended to provide training and professional development during this period, state “Nothing to Report.” For all projects reporting graduate student and/or post-doctoral participants, grantees are encouraged to describe how Individual Development Plans (IDPs) are used to help manage the training for those individuals. (up to 500-word limit)

The post-doctoral scholar at Purdue, Oguz Kaan Ozturk, and the graduate student at Ohio State, Andres Munos Salgado, received training and learned how to use various instruments, including scanning electron microscopy (SEM), rheometer, confocal laser scanning microscopy (CLSM), infrared spectroscopy (IR), differential scanning calorimetry (DSC), and texture analyzer. The trainings and experience on these instruments has helped both of them establish their careers, Mr. Salgado (M.S. student) took a research scientist position at ADM, Decatur, Illinois, and Dr. Ozturk has accepted a tenure-track assistant professor position at University of Illinois at Urbana-Champaign.

They also have had opportunities to attend technical conferences and meetings related to the project topic (plant-based proteins and analogues) and met with professionals both from industry and academia. Specifically, Dr. Ozturk attended the Conference of Food Engineering (COFE 2022), 2nd NIZO Plant Protein Functionality Conference (2022), and 16th International Hydrocolloids Conference (2022).

  - Please indicate the number of undergraduate and graduate students, post- doctoral scholars, or other educational components involved during this reporting period. If other education components are involved, please describe them in detail. (up to 500-word limit)

One post-doctoral scholar and one graduate student (M.S.) were involved in this project. There were no educational components in this project.

# Information Products

  - Please list the type(s) of information products (e.g., scholarly publications, reports or monographs, workshop summaries or conference proceedings, video, audio, images, models, software, curricula, instruments or equipment, intervention, etc.) produced during the project resulting directly from the FFAR award.

• One patent filing (filed on Apr 2023)

• 5 manuscripts – two published articles in the journal ‘Food Hydrocolloids’ (impact factor, 11.504), one under review in ‘Future Foods’, two in preparation for submission.

• Three conference abstracts (2022 Conference of Food Engineering (COFE), 2nd NIZO Plant Protein Functionality Conference, and 16th International Hydrocolloids Conference) – All accepted and presented.

  - Please provide a list of citations for the information products produced during the project.

• Salgado, A. M., Ozturk, O. K., Hamaker, B. R., Campanella, O. H. (2023). Matching textural properties of commercial meat and cheese products using zein as the viscoelastic agent and calcium hydroxide as the textural modifier in plant-based formulations. Food Hydrocolloids, 137, 108323.

• Ozturk, O. K., Salgado, A. M., Holding, D. R., Campanella, O. H., Hamaker, B. R. (2023). Dispersion of zein into pea protein with alkaline agents imparts cohesive and viscoelastic properties for plant-based food analogues. Food Hydrocolloids, 134, 108044.

• Ozturk, O. K., Salgado, A. M., Hamaker, B. R., Campanella, O. H. (2023). Zein-based food formulations. IP filing, 69649-01.

• Ozturk, O. K., Hamaker, B. R. (2023). Plant protein-based meat alternatives: Processing, base proteins, and other constructional ingredients. Future Foods (in revision).

• Ozturk, O. K., Salgado, A. M., Campanella, O. H., Hamaker, B. R., (202). Using zein as cohesive and viscoelastic agent in plant-based food analogues. 16th International Hydrocolloids Conference, Guelph, Ontario, Canada (Oral Presentation).

• Ozturk, O. K., Salgado, A. M., Campanella, O. H., Hamaker, B. R., (2022). Dispersion of zein into pea protein for cohesiveness and viscoelasticity in plant-based food analogues. 2nd NIZO Plant Protein Functionality Conference, online (Poster and Young Scientist Presentation).

• Ozturk, O. K., Salgado, A. M., Campanella, O. H., Hamaker, B. R., (2022). Engineering the textural properties of plant-based protein blends containing corn zein for food analogue products. Conference of Food Engineering, Raleigh, NC, USA (Oral Presentation).

  - Are there publications or manuscripts accepted for publication in a journal or other publication (e.g., book, one-time publication and monograph) during the project resulting directly from the FFAR award? If yes, please provide citation.

Yes, there are two publications already accepted. They are listed below. There is another in the revision process (included in the list in Section 3.2.)

• Salgado, A. M., Ozturk, O. K., Hamaker, B. R., Campanella, O. H. (2023). Matching textural properties of commercial meat and cheese products using zein as the viscoelastic agent and calcium hydroxide as the textural modifier in plant-based formulations. Food Hydrocolloids, 137, 108323.

• Ozturk, O. K., Salgado, A. M., Holding, D. R., Campanella, O. H., Hamaker, B. R. (2023). Dispersion of zein into pea protein with alkaline agents imparts cohesive and viscoelastic properties for plant-based food analogues. Food Hydrocolloids, 134, 108044.

  - Website(s). List the URL for any internet site(s) that disseminates the research activities. A short description of each site should be provided. It is not necessary to include the publications already specified above.

None other than journal publications.

  - Have inventions, patent applications, and/or licenses resulted from the project (U.S. and international)? If yes, indicate the invention, patent application(s), and/or license(s).

There is one recently submitted patent application (April 2023).

|  | # Filed (Enter Numeric Value) | # Approved (Enter Numeric Value) | Patent Numbers (Separated by commas) |
| --- | --- | --- | --- |
| Patents | #1 | #0 | 69649-01 |
| Copyrights | # | # |  |
| Trademarks | # | # |  |
| Inventions | # | # |  |

  - Are any of the information products produced during this grant that are confidential, proprietary, or subject to special license agreements? If so, please list them below and describe why they must remain confidential. Also, note if (and when) you plan to make these data publicly available in the future or if they must remain confidential indefinitely. (up to 500-word limit)

None

  - Beyond depositing information products in a repository, what other activities have you undertaken to ensure that others (e.g., researchers, decision makers, and the public) can easily discover and access the listed information products? What other activities have you undertaken to ensure that other can access and re-use these data in the future?

The published articles from this project include all the data we collected and can be accessed online by researchers and public.

We have also presented published parts of our results in technical meetings held by the Whistler Center for Carbohydrate Research at Purdue University, which has member companies from the food and agricultural industries. The Whistler Center allowed us to connect with industry working on plant-based protein area and our presentations in those meetings were uploaded in the Whistler Center website for member companies. The PI of the project, Bruce Hamaker, is director.

# Data Management

  - Did the project generate any data? Data generation includes transformation of existing data sets and data from existing resources (e.g., maps and imageries). Please list the data generated for the award.

Yes, the following is the list of the generated data: SEM and confocal images, data representing textural properties (extensibility, creep behavior, texture profile, large deformation behavior), rheological properties (amplitude sweeps, frequency sweeps), chemical properties (FT-IR spectra), physicochemical properties (moisture, pH, color parameters).

  - If you list multiple data sets, are these data sets related? If so, please provide a short description of how they are related.

Yes, they are related. Each of these data sets represent different aspects of the formulated blends’ functionality in terms of viscoelasticity and cohesiveness. SEM and confocal images provide visual observation of dispersion of zein into other constituents and the formation of a 3D viscoelastic network, while other tests exhibit the degree of viscoelasticity over small and large deformation conditions, and physicochemical and chemical properties of the blends. All together, they provided an overall view to understand how viscoelasticity and cohesiveness changed in the samples.

  - Please provide copies of relevant metadata records to support FFAR’s mission of enhancing the discoverability of FFAR funded project data and information products. Include or attach copies of records and a simple file inventory, if necessary, in a compressed folder.

No metadata records were generated for this project.

# Certification

The undersigned hereby certifies that to the best of their knowledge and belief, the above report and all supporting documents are true, accurate and complete. I am aware there is a significant penalty for submitting false or misleading information.

If applicable, I agree that my electronic signature is legally binding, equivalent to, and has the same validity and meaning as my handwritten signature. I will not claim otherwise.

PI Full Name: _Bruce R. Hamaker_____________________

PI Signature: ___________________________________ Date: _06/29/2023______

Authorized Signing Official (ASO) Name: Jason Spall

ASO Signature: _________________________________ Date: 06/30/23